## 2023 INTL PQM Rebuilds.
Site | Site POC | Sorter | Sorter ID | Chain Replacement | Chain Flip | Drive Shaft Replacement | Idler Shaft Replacement | Reducer Replacement | Driver Motor Replacement | Oiler Replacement | Repair Team | Project Date | Status | Dollar Value
LGA9 | Patrick Hoehn | AFE |  | X |  | X | X | X |  |  | INTL |  |  | 298139
CVG2 | Steve Ketron | SHP | OB909 |  |  | X | X | X |  |  | INTL | 2023-06-08 | Completed | 98386
IND5 | Kyle Boone | SHP |  | X and track |  | X | X | X | X |  | INTL |  |  | 118164
SAT1 | Jordan Hayes | RTE |  |  |  | X | X | X | X |  | INTL | 2023-09-15 | Completed | 160701
|  | SHP |  |  |  |  | X
HOU2 | Jason Dudley | RTE | 32010 |  | X | [5 empty] | PQM/RME | 2023-06-14 | 2023-06-14 | 180612
|  | AFE1 | 46010 |  | X | [6 empty] | 2023-06-15 | 2023-06-15
TUL2 | Jon Negaard | AFE2 | 46010 |  |  |  | X - 62351 |  |  |  | PQM/RME | 2023-05-16 | 2023-05-16 | 175050
|  | RTE | 32010 |  | X |  | X - 62351
DEN3 | Andrew Aragon | AFE2 |  |  |  |  | X - 62351 |  |  |  | PQM/RME | 2023-04-26 | 2023-04-26 | 42372
RDU1 | Brian Warren | AFE1 |  |  |  | X - 62352 | X - 62351 | X |  |  | PQM/RME | 2024 |  | 100461
CMH4 | Michael Milenovic | AFE2 |  |  | X | [5 empty] | PQM/RME | 2023-10-19 | 2023-10-19 | 90306
CVG9 | Josh Eskes |  | 31355 |  |  | X - 78945z | X - 78947z | 54179/24781 |  |  | PQM/RME | TBD 2024 Push |  | 394000
|  |  | 32360 |  |  | X - 78945z |  | 54179/24781
|  |  | 71040 |  |  | X - 78946z |  | 61733
|  |  | 72065 |  |  | X-78946Z | X-78947z | 61733/ 61732 =2
74050
|  |  | 33355 |  |  |  | X - 78947z
MKC6 | John Ungerer | RTE | 32010 |  |  | X - 62352 |  | X - 61733/61732 |  |  | PQM/RME | 2023-06-21 | 2023-06-21 | 64977
|  | SHP | 71010 |  | X | [6 empty] | 2023-03-09 | 2023-03-09 | 90306
DAL3 | Alex Villegas | RTE | 32010 |  | X | [5 empty] | PQM/RME | 2023-04-18 | 2023-04-18 | 90306
EWR9 | Visar Nerguti | RTE | 32010 |  | X | [5 empty] | PQM/RME | 2023-05-22 | 2023-05-22 | 90306
PCW1 | Nicole Ponstein | RTE | 32010 |  | X | [5 empty] | PQM/RME | 11/16/22 - 12 hour DTW | Completed | 90306
|  | AFE1 | 46010 |  | X | [6 empty] | 2023-03-07 | 2023-03-07 | 90306
YYZ7 |  | SHP |  |  | X | [5 empty] | PQM/RME | 2023-08-23 |  | 90306
Jobs added after the CAR was submitted
IGQ1 | Ryan Johnson | SHP | 71050 |  | X | [5 empty] | PQM/RME |  | Completed | 90544
CLE3 |  | AFE2 |  |  |  |  | X |  |  |  | PQM/RME | 2023-02-28 | Canceled by OPS | 47000
|  | AFE1 |  |  |  | X | X |  |  |  | PQM/RME | 2023-02-14 | 2023-02-16 | 97500
RDU1 |  | MRS | 32010 |  | X |  | X |  |  |  | PQM/RME | 2023-05-10 | 2023-05-10 | 132678
HOU6 |  | MRS1 |  |  | X | [5 empty] | PQM/RME | 2023-07-26 | 2023-07-26 | 90306
AZA5 |  | SHP | 71040 |  | X | X | X | X |  |  | PQM/RME | 2023-10-26 | 2023-10-19 | 191310
LIT1 |  | MRS2 | 32020 |  | X | [5 empty] | PQM/RME | 2023-11-15 | Completed | 90306
YYZ4 |  | AFE2 | 56106 |  | X | [5 empty] | PQM/RME | 2023-08-31 | Completed | 177832
AUS2 |  | SHP | 71050 |  | X | [5 empty] | PQM/RME | 2023-09-14 | Completed | 90306
SYR1 |  | SHP | 71050 |  | X | [5 empty] | PQM/RME | 2023-11-15 | Completed | 90306
MCO1 |  | MRS | 32010 |  | X | [5 empty] | PQM/RME | 2023-11-04 | 2023-11-04 | 90306
HOU6 |  | SHP | 71050 |  | X | [5 empty] | PQM/RME | 2024 |  | 90306
|  |  |  | Chain Replacement | Chain Flip | Drive Shaft Replacement | Idler Shaft Replacement | Reducer Replacement | Driver Motor replacement | Oiler Replacement
Totals: |  |  |  | 0 | 18 | 9 | 12 | 7 | 2 | 0
Key:
Parts in stock
Parts need ordered
Work is completed