## Sheet1
Row Labels | Count of Chain Flip | Count of Drive Shaft Replacement | Count of Idler Shaft Replacement | Count of Driver Motor replacement | Count of Oiler Replacement
INTL TEAM |  | 4 | 4 | 3
PQM TEAM | 16 | 12 | 10 | 2 | 1
Grand Total | 16 | 16 | 14 | 5 | 1
Row Labels | Sum of INTL Repair Costs | Sum of USD Approved Savings
INTL TEAM | 2653627 | 0
PQM TEAM |  | 3742503
Grand Total | 2653627 | 3742503

## 2024_Intellisort_Rebuilds_Cost_
Task ID | Created At | Completed At | Last Modified | Name | Assignee | Assignee Email | Start Date | Due Date | Projects | Parent task | Blocked By (Dependencies) | Blocking (Dependencies) | Sorter ID | Equip. ID | Shipping Address | Repair Team | Chain Replacement | Chain Flip | Drive Shaft Replacement | Idler Shaft Replacement | Reducer Replacement | Driver Motor replacement | Oiler Replacement | Black Track replacement | Slats | Oiler Upgrade Adder | Chain Care Adder | Chain cleaning | Dampener rings | INTL Repair Costs | USD Approved Savings | Total Projected Savings | Site POC | Planned Start Quarter | Shutdown times
1205632767421620 | 2023-10-02 | 2024-02-12 | 2024-03-06 | HOU6 | Ashlynn Maddox | maddoas@amazon.com |  | 2024-02-07 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | SHP | 71050 | Shorr HOU6 Non-Inventory Offsite 8805 Fairbanks North Houston Road Houston, TX 77064 United States Location Code: 289025247 Attn: RME Nacho Zapata/Andrew Le | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q1 2024 | 0600-0600
1205632767421620 | 2023-10-02 | 2024-11-11 | 2024-11-11 | RDU1 |  |  |  | 2024-11-07 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE2 | 46010 |  | PQM TEAM |  | X | X | X | X | [9 empty] | 229732 | 229732 |  | Q4 2023
1208502403173520 | 2024-10-08 | 2024-11-14 | 2024-11-14 | PCW1 |  |  |  | 2024-11-13 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS | 32010 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q4 2024
1205741659021930 | 2023-10-17 | 2024-03-11 | 2024-03-11 | LGA9 | Ashlynn Maddox | maddoas@amazon.com | 2024-03-08 | 2024-03-09 | 2024 Intellisort Rebuilds Cost Sheet,LGA9 AFE Chain, Drive, Idler and Reducer and Drive motor Replacement |  |  |  | AFE | 46010 | Amazon.com Services LLC (LGA9 NI) Lindenmeyer Munroe 200 Cascade Dr. Suite A Allentown, PA 18109 United States Location Code: 46320748 Attn: Mercy Taylor | INTL TEAM | X |  | X | X | X | [8 empty] | 296662 | 0 | 0 | hurnd@amazon.com | Q1 2024
1205741659021940 | 2023-10-17 | 2024-08-12 | 2024-08-12 | TPA2 | Ashlynn Maddox | maddoas@amazon.com | 2024-08-09 | 2024-08-11 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | SHP | 504 | 1760 S County Line Road Lakeland, FL 33811 ATTN: Paul Fleharty | INTL TEAM | X |  | X | X | X | X | [7 empty] | 785655 | 0 | 0 |  | Q3 2024
1205741659021940 | 2023-10-17 | 2024-08-12 | 2024-08-12 | TPA2 | Ashlynn Maddox | maddoas@amazon.com | 2024-08-09 | 2024-08-11 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE | 1209 | 1760 S County Line Road Lakeland, FL 33811 ATTN: Paul Fleharty | INTL TEAM | X |  | X | X | X | X | [7 empty] | 785655 | 0 | 0 |  | Q3 2024
1205741659021940 | 2023-10-17 | 2024-09-23 | 2024-10-03 | IGQ1 |  |  |  | 2024-09-18 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS1 | 32010 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q3 2024
1205741659021940 | 2023-10-17 | 2024-05-15 | 2024-05-15 | IND5 | Ashlynn Maddox | maddoas@amazon.com | 2024-05-09 | 2024-05-10 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | SHP | 5000 | Amazon.com Services, LLC c/o Premier Packaging 5055 W 79th St. Indianapolis, IN 46268 ATTN: AMAZON IND5 – ANDY KUKMAN | INTL TEAM | X |  | X | X | X | X | [7 empty] | 785655 | 0 | 0 |  | Q2 2024
1205887089320480 | 2023-11-08 | 2024-01-22 | 2024-02-23 | CVG9 |  |  | 2024-01-21 | 2024-01-24 | 2024 Intellisort Rebuilds Cost Sheet,CVG9 RTE 31355 Drive, Idler and Reducer Replacement |  |  |  | RTE | 31355 | Amazon CVG9 2305 Litton Lane Hebron, KY 41048 | PQM TEAM |  |  | X | X | X | [9 empty] | 112186 | 112186 |  | Q1 2024 | 12AM - 12AM
1205887089320480 | 2023-11-08 | 2024-01-22 | 2024-02-23 | CVG9 |  |  | 2024-01-21 | 2024-01-24 | 2024 Intellisort Rebuilds Cost Sheet,CVG9 RTE 32360 Drive & Reducer Replacement |  |  |  | RTE | 32360 | Amazon CVG9 2305 Litton Lane Hebron, KY 41048 | PQM TEAM |  |  | X |  | X | [9 empty] | 74463 | 74463 |  | Q1 2024 | 12AM - 12AM
1205887089320490 | 2023-11-08 | 2024-01-22 | 2024-02-23 | CVG9 |  |  | 2024-01-21 | 2024-01-24 | 2024 Intellisort Rebuilds Cost Sheet,CVG9 RTE 33355 Idler Shaft Replacement |  |  |  | RTE | 33355 | Amazon CVG9 2305 Litton Lane Hebron, KY 41048 | PQM TEAM |  |  |  | X | [10 empty] | 48747 | 48757 |  | Q1 2024 | 12AM - 12AM
1205887089320490 | 2023-11-08 | 2024-01-22 | 2024-02-23 | CVG9 |  |  | 2024-01-21 | 2024-01-24 | 2024 Intellisort Rebuilds Cost Sheet,CVG9 SHP 72065 Drive and Reducer Replacement |  |  |  | SHP | 72065 | Amazon CVG9 2305 Litton Lane Hebron, KY 41048 | PQM TEAM |  |  | X |  | X | [9 empty] | 74463 | 74463 |  | Q1 2024 | 12AM - 12AM
1205887089320490 | 2023-11-08 | 2024-02-12 | 2024-02-23 | HOU6 |  |  |  | 2024-02-07 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS2 | 32020 | Shorr HOU6 Non-Inventory Offsite 8805 Fairbanks North Houston Road Houston, TX 77064 United States Location Code: 289025247 Attn: RME Nacho Zapata/Andrew Le | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q1 2024 | 0600-0600
1205887089320500 | 2023-11-08 | 2024-02-12 | 2024-02-23 | HOU6 |  |  |  | 2024-02-07 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE | 56010 | Shorr HOU6 Non-Inventory Offsite 8805 Fairbanks North Houston Road Houston, TX 77064 United States Location Code: 289025247 Attn: RME Nacho Zapata/Andrew Le | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q1 2024 | 0600-0600
1205887089320500 | 2023-11-08 | 2024-09-13 | 2024-09-13 | JAX2 |  |  |  | 2024-09-10 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE1 | 46010 |  | PQM TEAM | X |  | X | X | X | X | [8 empty] | 397073 | 397073 |  | Q4 2024 | 0600-0600
1205887089320510 | 2023-11-08 | 2024-06-24 | 2024-06-24 | JAX2 |  |  | 2024-06-19 | 2024-06-21 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE2 | 56010 |  | PQM TEAM | X |  | X | X | X | X | [8 empty] | 397073 | 397073 |  | Q2 2024 | 0600-0600
1207791812698760 | 2024-07-11 | 2024-07-11 | 2024-10-08 | BOS3 |  |  |  | 2024-07-04 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS | 32010 |  | PQM TEAM |  |  | X |  | X | [9 empty] | 74463 | 74463 |  | Q3 2024
1207790526101660 | 2024-07-11 | 2024-07-11 | 2024-07-11 | SAT3 |  |  |  | 2024-07-11 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS | 46010 |  | PQM TEAM |  | X |  |  |  |  | X | [7 empty] | 155127 | 155127 |  | Q3 2024
1205887089320510 | 2023-11-08 | 2024-11-07 | 2024-11-07 | KCVG |  |  |  | 2024-11-06 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | RTE | 2012110401 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q2 2024
1205887089320520 | 2023-11-08 | 2024-09-23 | 2024-10-03 | DEN3 |  |  |  | 2024-09-17 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE2 | 56010 |  | PQM TEAM |  |  | X |  | X | [9 empty] | 74463 | 74463 |  | Q3 2024 | 0600-1800
1205887089320520 | 2023-11-08 | 2024-06-10 | 2024-06-24 | DEN3 |  |  |  | 2024-06-05 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS | 32010 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q2 2024 | 0600-1800
1208468690590080 | 2024-10-03 | 2024-10-03 | 2024-10-08 | DEN3 |  |  |  | 2024-09-17 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS | 32010 |  | PQM TEAM |  |  |  | X | [10 empty] | 48747 | 48747 |  | Q3 2024
1205887089320650 | 2023-11-08 | 2024-04-23 | 2024-10-08 | BFL1 | Ashlynn Maddox | maddoas@amazon.com |  | 2024-04-18 | 2024 Intellisort Rebuilds Cost Sheet,BFL1 AFE1 Chain Flip |  |  |  | AFE2 | 56010 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q2 2024
1205887089320530 | 2023-11-08 | 2024-02-29 | 2024-03-13 | CMH4 |  |  |  | 2024-02-29 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS | 32010 | AMAZONCOM SERVICES LLC ATTN: CMH4 MAINTENANCE 785 FREBIS AVE COLUMBUS, OH 43206-3707 | PQM TEAM |  | X | X | X | X | [9 empty] | 229732 | 229732 |  | Q1 2024 | 06:30am-0630am
1205887089320530 | 2023-11-08 | 2024-02-29 | 2024-02-29 | CMH4 |  |  |  | 2024-02-29 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE2 | 56010 | AMAZONCOM SERVICES LLC ATTN: CMH4 MAINTENANCE 785 FREBIS AVE COLUMBUS, OH 43206-3707 | PQM TEAM |  |  | X | X | X | [9 empty] | 112186 | 112186 |  | Q1 2024 | 06:30am-0630am
1205887089320540 | 2023-11-08 | 2024-08-12 | 2024-08-12 | ACY1 |  |  | 2024-08-07 | 2024-08-09 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS | 32010 |  | PQM TEAM |  |  | X | X | X | [9 empty] | 112186 | 112186 |  | Q2 2024
1205887089320540 | 2023-11-08 | 2024-08-12 | 2024-08-12 | ACY1 |  |  | 2024-08-07 | 2024-08-09 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE1 | 56010 |  | PQM TEAM |  | X | X | X | X | [9 empty] | 191310 | 191310 |  | Q2 2024
1205887089320550 | 2023-11-08 | 2024-02-23 | 2024-02-23 | MQY1 |  |  |  | 2024-02-22 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS2 | 32020 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 | nardjoho@amazon.com | Q1 2024
1205887089320550 | 2023-11-08 | 2024-02-23 | 2024-02-23 | MQY1 |  |  |  | 2024-02-22 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | SHP | 71050 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 | nardjoho@amazon.com | Q1 2024
1205887089320560 | 2023-11-08 | 2024-10-27 | 2024-10-27 | MCO1 |  |  |  | 2024-10-24 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | AFE1 | 46010 |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q3 2024
1208287803581160 | 2024-09-11 | 2024-10-31 | 2024-10-31 | BDL4 |  |  |  | 2024-10-29 | 2024 Intellisort Rebuilds Cost Sheet |  |  |  | MRS |  |  | PQM TEAM |  | X | [12 empty] | 117546 | 117546 |  | Q4 2024 | 06:00-18:00