## DEN3
Positive and Negative experiences: successful practices and areas for improvement | Root Cause: identify the root causes of both successes and failures | Context: Describe the project background, objectives, constraints, and any other relevant information | Recommendations: actionable recommendations based on the lessons learned | RASCI: Assign responsibilities
the SIm ticket submitted was for 12 hours nor 24 and the scope of work required 24 to complete | comunication between the PM and the Site POC on the DTW needed was miscommunicated |  |  | PM responsibility
site gave Carey the lead tech a radio | Radio for PQM lead helps the leader on site connect and stay aligned. Not always needing to connect over the chime rasining concerns for all other stakeholders who are not at the rebuild |  | Identify a radio channel and add an asana step
PTP on APM or EAM. The site let us know in advance that they were on APM |  |  | Asana update | provide site with a link (action plan review meeting) to print out the PTP
Clear bag policy at the site was announced two days before the repair |  |  | Asana update | Speak with the site about this (enforced or not enforced)
It was a challenge to get in contact with the team at times both on slack and chime to manage parts at the site, the red lockout box and other concerns that werent looked at until hours later | Having a better way of communicating with the site team |  | PM should have the POC at the site phone numbers to stay in contact with the team throughout the repair and for any concerns | PM responsibility
There were parts that were not pulled and staged until I came on site. Majority of the team didnt know there was a major repair taking place at the site that week | Not having enough site contacts involved in the repair process |  | Moving forward all sites should ahve at the very least 5 site contacts involved in the process for the rebuild or major repair with the meeting notes and escalations reaching the RMM and GM | PM responsibility
PM sent the wrong time for the technicians to arrive to the site (5:30 instead of 4:30 AM) | alignment on the times for the repair | times change based on the repair and site so alignment on this is necessary for all repairs moving forward | Moving forward all repairs should have an alignment meeting Asana update and align | PM responsibility
PM did not account for the plywood at the site | Alignment on the tools needed for each repair | Tools and even parts can change based on the site and repair being done so it is important to align with the SME and PQM Manager on what is needed for each repair | Moving forward all repairs should have an alignment meeting Asana update and align | PM responsibility
reducer model number was not correct and we could not complete the AFE2 repair | PM needed to make sure all reducers at the site are the correct reducer by checking the model number and making sure all parts are photo verified with the team and submitted in the pre repair report for cloiser inspection | A new reducer is needed for drive shaft replacements. The reducer needed was not at the site. | Check the model number for all reducers and verify with the team if they are correct update the safety culture | PM responsibility
Job plan to review the parts | The site team requested a job plan to review all parts to ensure they are correct
Having the shutdown during the same week as other major projects | The APM and repair were within hours of each other |  | Update the asana with this item

## JAX2
Positive and Negative experiences: successful practices and areas for improvement | Root Cause: identify the root causes of both successes and failures | Context: Describe the project background, objectives, constraints, and any other relevant information | Recommendations: actionable recommendations based on the lessons learned | RASCI: Assign responsibilities
Need to have enough slats and end caps to adjust for chain stretch |  | JAX2 had 4 broken endcaps and we needed to add slats to the sorter during the repair | we need to have 25 brand new slats on site and ready with new chain rebuilds to adjust for broken and filled in slats In meeting 1 we go over the request of what the site has and are aware of what we need ( we can send out from CRW1 and have the site purchase new slats and send to CRW1) call out of PMQ and INTL full sorter rebuilds
There was not enough simple green for cleaning stations and they had five gallon jugs (they had blue barrels from safety already set up) | we need cleaning stations set up with multiple hand held spray bottles |  | update the template with the requirements (10 bottles to a station) and plenty of rags site to provide the safety HAZMAT barrels ready and review this with the site on a call (meeting 2) | PM
Training room reserved for full sorter rebuilds? |  |  | always reserved for a full rebuild only the team should meet at the training room before the shift
Shuttles for chain to be removed/ dumpsters | We can use cut down shuttles for the chain removal |  | Make sure the sites have the 48 inch shuttles / cut down the 72 inch to 48 add to the template
#1 BTA , will it be replaced on all full sorter rebuilds |  |  | standard to check
LOTO control Log needs to be on asana template and for all sorter rebuilds |  |  | group lock box standard
When sending out the Labor solicitation emails we should also send out the slack URL for techs who are signing up for the rebuild
motion had defective chain (manufacturing defect) |  |  |  | motion is putting a QC measure in place so this doesnt happen again they will have an open invite to come to Georgia to walk around the plant etc.
standard 40x40 for the slat stacking |  |  | make sure this is in the PVQ and review in the meeting 2
pre rebuild walk a few weeks before the repair |  |  | add to the template that PQM does a walk through the building for the repair/ pick apart the plan for each rebuild ( can do a pre audit in this walk)
Work order |  |  | One work order for the full rebuild to designate the PTP for the entirety of the rebuild for one sorter (future idea is to work with the APM team to have sorter rebuild work orderes only submitted by teh rebuild team)

## IND5
Positive and Negative experiences: successful practices and areas for improvement | Root Cause: identify the root causes of both successes and failures | Context: Describe the project background, objectives, constraints, and any other relevant information | Recommendations: actionable recommendations based on the lessons learned | RASCI: Assign responsibilities
Two days before the rebuild the site team had to complete the avetta form to submit the project properly through Amazon. We had to get the INTL team to submit forms through Avetta in a short time frame. |  | The avetta form needs to be completed to do this project / rebuild at the site | Obtain the JHA form earlier in the process and have the site submit the avetta form at an earlier date. This can be done by adding this step to the template and ensuring the work is completed within a certain time frame make sure the INTL team has all rigging certificates/ pit and man lift we had but ensure they are there as well | PM can do
having the post evaluation on Asana completed and filled out | I had the role attached to this tasks as SME | This is here to have a post evaluation attached to the asana to track that the rebuild went well during the start up and the team is aligned on closing out the project (we wont need anything else from INTL or the PQM team) | this needs to be assigned to the SMM or AMM that is on site the day of and after the rebuild | reassign to SMM and make sure to align on roles and responsibilities before the rebuild/during meetings
David and Carl came in the day before the rebuild | Did a site walk with the Amazon site safety team and allowed questions to be asked and answered walked through and figured out the dock door to be used |  | site safety and INTL safety can work together onsite for the site walk
cleaning supplies ran out |  |  | make sure the site has extra cleaning supplies in case

## TPA2
Positive and Negative experiences: successful practices and areas for improvement | Root Cause: identify the root causes of both successes and failures | Context: Describe the project background, objectives, constraints, and any other relevant information | Recommendations: actionable recommendations based on the lessons learned | RASCI: Assign responsibilities

## MCO1
Positive and Negative experiences: successful practices and areas for improvement | Root Cause: identify the root causes of both successes and failures | Context: Describe the project background, objectives, constraints, and any other relevant information | Recommendations: actionable recommendations based on the lessons learned | RASCI: Assign responsibilities

## ACY1
Positive and Negative experiences: successful practices and areas for improvement | Root Cause: identify the root causes of both successes and failures | Context: Describe the project background, objectives, constraints, and any other relevant information | Recommendations: actionable recommendations based on the lessons learned | RASCI: Assign responsibilities